## Summary
SHARK BAY — Bitterns Recycling Field Piping Installation
Client: Shark Bay Resources (SALT) · PO-182113 · 30 D FIME · Delivery 30 Oct 2026
GROSS MARGIN — FORECAST vs ACTUAL
| FORECAST GM % | ACTUAL GM % |  | VARIANCE (pp)
20%
| what we quoted it at (type here) | live: (received − 2iB cost) ÷ received |  | actual − forecast
POSITION (auto from 2iB + your claims)
Actual cost to date (2iB invoiced) |  |  | 0
Committed cost (2iB POs raised) |  |  | 362252.09
Revenue received to date
Revenue invoiced to date
NET CASH ON JOB (received − actual cost) |  |  |  |  | ◄ keep ≥ 0
Contract value (ex GST) | 2789004.51 |  | 2789004.51
Forecast cost (contract × (1−fcst GM))
Forecast profit $
Cost feed: 2iB_Report_-_PO_Detail_Report_-_Raw_-_20260714-1502.csv · 6 Shark Bay PO lines matched

## Tracker
COST, PROGRESS & MARGIN TRACKER — blue cells are yours (Cost Budget · Actual Cost · % Complete); job totals auto-fill from 2iB
Item | Description | Qty | UOM | Contract Sell (ex GST) | Cost Budget (input) | Actual Cost (input/2iB) | Cost var (bud−act) | % Comp | Revenue earned | Margin to date | Mgn % | Flag
1 Project Management & Preliminaries
1.1 | PM, Supervision, Admin & Overheads | 1 | Lump Sum | 243432
1.2 | Site Facilities (Site Hub — renewable powered) | 1 | Lump Sum | 25725
Project Management & Preliminaries — subtotal
2 Supply
2.1 | Contractor Supply as per SOW | 1 | Lump Sum | 1001335.37
2.2 | Stand Pipe Opt 1 316SS SCH 40 | 2 | Each | 37164
2.3 | Stand Pipe Off Take Tee 560-110 | 2 | Each | 16780
2.4 | Additional Drain Off Take 560-355V | 1 | Each | 7580
Supply — subtotal
3 Mobilisation / Setup / Demobilisation
3.1 | Mobilisation | 1 | Lump Sum | 76510.72
3.2 | Demobilisation | 1 | Lump Sum | 54367.72
3.3 | Freight of Equipment Return | 1 | Lump Sum | 71064
Mobilisation / Setup / Demobilisation — subtotal
4 Site Installation Works
4.1 | Unloading of Pipe — 58 trucks | 1 | Days | 85176
4.2 | 3,000m of 560 PN8 PE100 SDR21 | 1 | Days | 49826.7
4.3 | 14,800m of 560 PN6.3 PE100 SDR26 | 1 | Days | 298145.4
5.0 | 3,200m of 560 PN10 PE100 SDR21 | 1 | Days | 54362.7
4.4 | 750m of 355 PN8 PE100 SDR17 | 1 | Days | 9147.6
4.5 | Road Crossings x 10 | 1 | Days | 108595.2
4.6 | ARV Tie In's 560 | 1 | Days | 62130.6
4.7 | Flush Water Tie In | 1 | Days | 6293.7
4.8 | Earth Mounding | 1 | Days | 55692
4.9 | Flow Meters / Actuated Valve / Scour Drain Tee | 1 | Days | 39138.75
5.1 | Install 2x Standpipe | 1 | Days | 21404.25
Site Installation Works — subtotal
6 Other
6.1 | Pre-Contract Legal Costs | 1 | Lump Sum | 20000
6.2 | Survey | 1 | Days | 28576.8
6.3 | Freight of Pipe — 58 Trailers (Perth) | 1 | Lump Sum | 416556
Other — subtotal
CONTRACT TOTAL (PO-182113)
Check vs PO ($2,789,004.51):
| 2iB job actual cost (auto): |  |  | 0

## Invoicing
INVOICING & PROGRESS CLAIMS — 30% now (mob+materials) → bulk end of month 2 → progress to completion
Claim # | Description | Amount ex GST | GST | Total incl GST | Received (input) | Date invoiced | Due (30 FIME) | Date paid | Status
Claim 1 | Mobilisation + materials deposit + preliminaries (≈30%) | 836701.35 |  |  |  | Jul 2026 | ~30 Aug 2026
Claim 2 | All materials supplied + mobilisation + progress claim |  |  |  |  | end Aug 2026 | ~30 Sep 2026
Claim 3 | Progress claim — installation works |  |  |  |  | Sep 2026 | ~30 Oct 2026
Claim 4 | Final — completion, demob & retention release |  |  |  |  | Oct 2026 | ~30 Nov 2026
TOTAL CLAIMS
Reconcile to contract $2,789,004.51:

## Discrepancies
DISCREPANCIES, VARIATIONS & CLAIMS LOG — estimate vs PO, cost over-runs, variations
Ref | Item / issue | Estimate $ | PO $ | Δ variance | Status / action
6.4 | Weather Standdown — Personnel & Equipment | 33661.15 | 0 |  | In estimate, EXCLUDED from PO — raise as a variation/claim if a weather standdown is incurred.